Emergency Centre for Locust Operations (ECLO) Situation Report – No 5 6 November – 12 November 2004

1. Meeting of Desert Locust-affected Northern African countries

The Ministers of Agriculture of Algeria, Libya, Mauritania, Morocco, and Tunisia met in Tunis on the 6 November 2004. They discussed the current Desert Locust situation prevailing in the five countries, involving the invasion of the sub-region by many swarms produced during the summer breeding season in the Sahel.

The Ministers of Agriculture launched an urgent appeal for US$91 million for assistance from the international donor community.  The countries themselves expect to contribute  US$101 million from their own resources.

The Ministers of Agriculture requested FAO to continue its efforts with donors and regional/international organizations to raise the funds needed to control the Desert Locust.

1.1 Plan of Action

The Ministers of Agriculture also agreed on a Plan of action and propose a two-phase approach focusing on:

  - Phase I: Northern Mauritania (US$40 million): an intervention against locust populations that may breed during the winter in northern Mauritania (to treat 2 million hectares at US$20/per hectare), if good rains fall in this area.

  - Phase II: Algeria, Libya, Morocco and Tunisia (US$192 million): estimated  needs for a possible further  intervention should there be widespread breeding of Desert Locusts in the spring of 2005.

1.2 Resources available through FAO

To date, FAO has the following project funds available and/or pledged for the procurement of pesticides, flying hours and equipment:

- North Africa       : US$4.6 million

For North Africa, these amounts have already been allocated to the most urgent needs identified by affected countries.

To guide donors, FAO has prepared a summary (see Annex I) of supplies (logistics and services) urgently needed for locust survey and control operations, totalling  US$2 671 500.

These requirements will be regularly revised as the situation evolves on the ground during the winter and spring campaign in North Africa.

FAO will continue to work in close cooperation with the Mauritanian authorities to establish their specific urgent needs, depending also on how the winter breeding develops, and will  provide this information to donors.  At present, US$7.6 million remain in the balances of funds received from donors and allocated to Mauritania. Some of this total is planned for use in the 2005 summer season. If it becomes necessary to use it all for the winter campaign, additional resources will need to be identified for summer 2005.

2. Planning for the 2005 Sahel campaign

- With regard to interventions in the Sahel, FAO is currently formulating a detailed plan of activities with a view to pre-positioning components as early as possible bearing in mind that requirements will depend on the further development of the upsurge and, therefore, will not be known before March-April 2005.  Plans for the 2005 summer campaign will be ready by April 2005.

- Meanwhile locust survey and control operations will continue in northern parts of the Sahel. Early in 2005, a training programme will be launched to strengthen capacity before the summer season starts in July.

- To date, resources available for control operations in the Sahel amount to US$ 8.6 million for pesticides and US$6 million for flying hours.

3. Overview of the situation

- Intensive aerial and ground control operations continued in Morocco and Algeria against immature swarms arriving from summer breeding areas in the Sahel in West Africa.

- In Mauritania, a few of the swarms are beginning to mature, but the great majority remain immature. Control operations are in progress in the south and centre.

- Smaller infestations are present in northern Mali and Niger.

- The situation has returned to normal in Burkina Faso and Chad. Senegal has not seen any swarms since 5 November.

- Several swarms that arrived on the Mediterranean coast in Egypt have drifted further east and invaded farms between Cairo and Alexandria.

- The locusts that initially arrived on the coast of Cyprus, Israel and Lebanon were controlled, but new swarms may have reached Cyprus following further days of warm southerly winds.

- The situation should continue to improve in West Africa but it is likely to deteriorate further in Northwest Africa as more swarms arrive during this month.

- Local breeding is underway on the Red Sea coast in Yemen, but has no connection with events in West Africa.

4. Crop and Food Supply Assessment Mission: mixed picture in the Sahel

- Overall, agricultural production in the nine Comité Permanent inter-États de lutte contre la sécheresse (CILSS) countries is expected to be close to the five-year average. However, the country-by-country situation varies. Mauritania, which is already beset by several years of unfavourable rainfall and low production, has born the brunt of Desert Locust damage -- the swarms stayed there much longer than anywhere else. Cape Verde will be facing a larger than usual food deficit but suffered little loss due to locusts.

- Many of the northern parts of the agricultural belt in the Sahel suffered from a combination of drought and locust attacks. Pastoral and agro-pastoral groups have been especially hard hit. With scarce pasture and water, the early movement of livestock herds has already started, leading to serious confrontations over the limited grazing available in many areas. Urgent action is needed to establish safe passage areas for livestock and to vaccinate animals on their way to southern pastures.

- In addition to food assistance to the most vulnerable populations, many farming families will need seeds and other inputs for off-season agriculture, and even for the next main growing season.

- Continued monitoring and preparation for Desert Locust control in 2005 is also needed; if there is good rainfall, swarms are likely to return to the Sahel next year unless winter/spring control in North West Africa is fully effective.

5. Funding situation

As of 12 November 2004, FAO has received US$55.6 million in cash, to which the organization has added US$6 million of its own funds. US$11.5 million has been pledged but not yet received US$5.4 million is currently being negotiated with donors.

6. Assistance provided through FAO

6.1. Aircraft

FAO has arranged for two spray aircraft to be released early from Senegal, so that they can work in Mauritania from 14 November, bringing the total number of FAO aircraft working there to six.

6.2 Human Resources

The Senior Locust Officer at the regional Emergency Coordination Unit (ECU) in Dakar visited Guinea-Bissau (from 3 to 5 November 2004) to identify short term needs and order equipment for locust survey  and ground control. Up to now, Guinea-Bissau has not received any locusts and is now unlikely to do so until next summer.

6.3. Area treated

From 1 to 10 November 2004, Morocco has sprayed 405 456 hectares.

Table 1: Area treated in hectares by country, as of 12 November 2004*

| Country | Current month and/or latest information available | Cumulative total since July 2004(*2) |
| --- | --- | --- |
| Algeria | 131 745 (1 - 31 Oct.) | 134 545 |
| Burkina Faso | 3 839 (1 - 20 Oct.) | 16 286 |
| Cape Verde | 236 (Nov.) | 1 249 |
| Chad | 2 000 (23 Sept. – 2 Oct.) | 8 801 |
| Egypt | 60 (30 Oct.) | 1 859 |
| Libya | 4 925 (1 - 31 Oct) | 5 985 |
| Mali | 106 582 (1 - 20 Oct.) | 347 351 |
| Mauritania | 446 541 (Nov.) | 687 244 |
| Morocco | 405 456 (5 – 12 Nov) | 865 000 |
| Niger | 1 000 (1 - 31 Oct.) | 200 880 |
| Senegal | 35 797 (Nov.) | 686 351 |
| Tunisia | 14 255 (18 Oct. 1 Nov.) | 14 255 |
| Yemen | 175 (1 - 4 Oct.) | 175 |
| TOTAL | 1 152 613 | 4 540 489 |

* Most recent reports. Reporting delays and discrepancies may affect the accuracy of these figures. (*2)These numbers represent spraying operations against Desert Locust originated from the Sahel.

7. Bilateral

- Burkina Faso provided Mali with 5 000 litres of pesticides and three ground teams.

- The six USAID aircraft that had been conducting spraying operations in Senegal (and to a lesser extent in Southern Mauritania) left Senegal on Wednesday, 10 November 2004.

Disclaimer: Information contained in the paragraphs relating to bilateral information is not exhaustive. It depends entirely on what is reported to FAO on bilateral assistance from a variety of sources. FAO cannot take responsibility for accuracy of the information provided by external sources. Countries and donors wishing to provide additional information are strongly encouraged to do so by sending an email to the following address: locusts-assistance@fao.org

8. World Bank

- Between 1 and 3 November 2004, the World Bank met with the governments of the Sahelian countries affected by the Desert Locust (Burkina Faso, Chad, the Gambia, Mali, Mauritania, Niger and Senegal).

- The FAO Regional Office for Africa and FAO consultants were involved in some of the technical discussions.  During these meetings, the affected countries were requested to present their needs related to US$60 million in World Bank credits being provided to strengthen national locust control efforts.

- By the end of the week the World Bank was negotiating soft loans bilaterally with the affected countries.

| Information The latest information on the Desert Locust situation, operational activities and donor funding can be found on FAO’s locust web site: (http://www.fao.org/news/global/locusts/locuhome.htm) |
| --- |
| Hilde Niggemann Operations Officer Emergency Operations and Rehabilitation Division ECLO FAO, Rome | Clive Elliott Senior Officer Locust and Other Migratory Pests Group Plant Production and Protection Division ECLO FAO, Rome |
| For further information, please contact these persons at the following email address: locusts-assistance@fao.org |

ANNEX 1

Summary Table: Urgent needs identified in selected North-African countries

Algeria

| ITEMS | NEEDS | Covered by FAO projects funded by other donors | Remaining – Still to be funded |
| --- | --- | --- | --- |
|  | Quantity | US$ | Quantity | US$ | Quantity | US$ |
| Radio Codan | 100 units | 600,000 | 50 units | 300,000 | 50 units | 300,000 |
| PSION Computer | 100 units | 70,000 | 40 units | 28,000 | 60 units | 42,000 |
| GPS | 1000 units | 300,000 | 246 units | 74,000 | 754 units | 226,000 |
| Cholinesterase kit | 200 bases + 800 reagent | 560,000 | 20 bases + 80 reagent | 56,000 | 180 bases + 720 reagent | 504,000 |
| Prospecting kit | 200 units | 19,000 | 100 units | 9,500 | 100 units | 9,500 |
| Atropine kit | 1000 units | 50,000 | 500 units | 25,000 | 500 units | 25,000 |
| Total |  | 1,874,000 |  | 767,500 |  | 1,106,500 |

Morocco

| ITEMS | NEEDS | Covered by FAO projects funded by other donors | Remaining – Still to be funded |
| --- | --- | --- | --- |
|  | Quantity | US$ | Quantity | US$ | Quantity | US$ |
| Pesticides | 300,000 litres | 2,225,000 | 260,000 litres | 1,950,000 | 40,000 litres | 275,000 |
| Flying Hour | 700 hours | 1,540,000 | 176 hours | 389,000 | 524 hours | 1,151,000 |
| Total |  | 4,050,000 |  | 2,624,000 |  | 1,426,000 |

Tunisia

| ITEMS | NEEDS | Covered by FAO projects funded by other donors | Remaining – Still to be funded |
| --- | --- | --- | --- |
|  | Quantity | US$ (estimates) | Quantity | US$ (estimates) | Quantity | US$ (estimates) |
| Pesticides | 100,000 litres | 641,000 | 96,600 litres | 625,000 | 3,400 litres | 16,000 |
| ULV Sprayer | 200 units | 246,000 | 100 units | 123,000 | 100 units | 123,000 |
| Total |  | 1,198,500 |  | 1,059,500 |  | 139,000 |

| Grand total | US$ 2,671,500 |
| --- | --- |